## Start here
Billing readiness tracker
From RunByOps guide 03: When finished jobs sit waiting for paperwork before they can be invoiced. Free to use and change.
A queue of every job where the work is finished but the invoice hasn’t gone, with what’s missing, who’s getting it and by when. Review it weekly, oldest first.
How to use it
1. On the Requirements tab, replace the examples with what each of your job types needs before billing. Take them from your agreed scopes, your customers’ processes and your terms, not from memory.
2. On the Queue tab, add every job where the work is complete but there’s no invoice yet. Name the missing items, one owner and a follow-up date for each.
3. Days waiting is worked out for you: from work complete to the ‘As at’ date (today), or to the invoice date once there is one. Change ‘Escalate after (days)’ beside the table to suit. The formula is filled in for the first 60 rows; copy it down if you need more.
4. Once a week, sort by Work complete, oldest first, and work through the Weekly review tab.
The five stages
1. Work complete. The work in the agreed scope is physically finished. Moved on by whoever did the work, by recording it.
2. Documentation complete. Everything this job type needs is in the record. Moved on by the job’s owner, chasing anything missing.
3. Ready for billing review. Queued for a check against the scope, approvals and the customer’s terms. Moved on by whoever reviews billing.
4. Invoice issued. Sent in the format and through the channel the customer requires. Moved on by accounts.
5. Paid. Payment received and matched to the invoice.
On hold. Waiting on a decision or a dispute. Record the reason and an owner, so held jobs don’t distort the queue.
What the colours mean
Pink follow-up: overdue. Yellow days waiting: past your escalation limit. Pink missing items: still missing. Green stage: ready for billing review.
Limits
This tracker shortens the gap between finishing and invoicing. It doesn’t guarantee payment and it doesn’t create revenue. It isn’t legal or accounting advice: what you can bill, and when, depends on your contracts and terms.
The Requirements examples and the Example tab are illustrative: invented jobs, customers, requirements and dates. Replace or delete them.

## Requirements
EXAMPLES TO REPLACE: illustrative requirements. Yours come from your own scopes, customer processes and terms.
Job type | Required before billing | Comes from | Notes
Strata call-out | Work order or PO number | Customer process | Ask for it at booking
Strata call-out | Attendance date and times | Terms
Strata call-out | Before and after photos | Customer process
Strata call-out | Signed job sheet or completion note | Agreed scope | Get it on site, before the job is marked complete
Strata call-out | Written approval for any extra work | Terms
Delivery run | Booking reference | Customer process
Delivery run | Signed or photo proof of delivery for every drop | Agreed scope
Delivery run | Waiting time recorded | Terms | Only if your agreement makes it chargeable
Delivery run | Exceptions noted: damaged, refused or part-delivered | Agreed scope
Inspection | Report reviewed and issued | Agreed scope
Inspection | Access and limitations recorded | Agreed scope
Inspection | Client acceptance | Terms | Only if your terms require it
Repair | Quote acceptance | Agreed scope
Repair | Completion photos | Customer process
Repair | Written approval for any extra work | Terms

## Queue
Job reference | Customer | Job type | Work complete | Stage | Missing items | Owner | Follow-up | Days waiting | On hold reason | Invoice no. | Invoice date | Paid date | Notes | Escalate after (days) | 14
As at

## Weekly review
Weekly review
Twenty minutes, same time each week. Sort the Queue by Work complete, oldest first, and work down the list.
For each job
☐ What’s missing? Is it named specifically?
☐ Who’s getting it, and when? One person, one date.
☐ Is it stuck on something we need to decide: a dispute, unapproved extra work, a customer who’s gone quiet? If so, set it to On hold with a reason and an owner.
☐ Does it now meet its requirements? Move it to Ready for billing review.
☐ Has it passed the escalation limit? Decide who escalates, and to whom.
Before invoicing
☐ Everything in the agreed scope is done and evidenced.
☐ Extra work is approved in a form you can file.
☐ The invoice matches the customer’s format, channel and reference requirements.
Then
☐ Which item was missing most often this week? If it keeps coming up, fix it where it’s captured: on site, or at booking.
Review log
Date | Jobs waiting | Oldest (days) | Most common missing item | Fix at the source

## Example (illustrative)
ILLUSTRATIVE EXAMPLE: the queue from guide 03, as at Monday 14 September. Invented jobs, customers and dates. Delete this tab when you start.
Job reference | Customer | Job type | Work complete | Stage | Missing items | Owner | Follow-up | Days waiting | On hold reason | Invoice no. | Invoice date | Paid date | Notes | Escalate after (days) | 14
J-2398 | Example Strata, for 30 Sample Rd | Strata call-out | 2026-09-02 | Work complete | PO number from the strata manager | Office admin | 2026-09-11 | [5 empty] | Next time, ask for the PO number at booking | As at | 2026-09-14
J-2403 | Warehouse customer, 40 Demo Way | Delivery run | 2026-09-04 | Work complete | Proof of delivery for drop 3 of 4 | Dispatch | 2026-09-15 | [5 empty] | If the driver has no photo, ask the receiver to confirm in writing
J-2405 | Owners corporation, 5 Example Pl | Inspection | 2026-09-07 | Work complete | Report review | Senior inspector | 2026-09-16 | [5 empty] | Review booked for Wednesday
J-2417 | Example Strata, for 12 Example St | Repair | 2026-09-10 | Work complete | Written approval for the extra sealant work | Office admin | 2026-09-15 | [5 empty] | Invoice agreed scope now, extra work once approved, if terms allow
J-2412 | Example Strata, for 30 Sample Rd | Strata call-out | 2026-09-11 | Ready for billing review |  | Accounts | 2026-09-14 | [5 empty] | Check against the work order, then invoice

## Lists
Stage | Job type | Edit these lists to match your business. The drop-downs use rows 2 to 30.
Work complete | Strata call-out
Documentation complete | Delivery run
Ready for billing review | Inspection
Invoice issued | Repair
Paid | Other
On hold